## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Day 1 | Day 2 | Day 3 | Day 4
That User Story | Code Things…
So that the user can choose what they want to do | Design main UI and add necessary buttons | 1
So that users can register their account | Design registered Users UI | 1
So that users can register their retirement homes | Design registered homes UI | 0.5
So that users can add themselves to the registered user list | Code a method to add users with valid credentials to the list | 2
So that users can add their homes to the registered homes list | Code a method to add homes with valid address to the homes list | 2
So that users can enter their credentials | Add a window for user registration that takes email and name | 0.5
So that users can enter the details for their home | Add a window for home registration | 0.5
So that users can submit or cancel their registration | Code a method that adds or canels the user registration | 2
So that users can submit or cancel their home registration | Code a method that adds or cancels the home regristation | 2
So that users can remove their home from the list | Code a method to remove a user from the account list | 1
So that users can remove their user account | Code a method to remove a home from the home list | 1
So that users can register their account | Connect the add button to the add method | 0.25
So that users can register their account | Connect the cancel button to the cancel method | 0.25
So that users can submit or cancel their registration | Code an error message if the credentials are not valid | 0.5
So that users can submit or cancel their home registration | Code an error message if the credentials are not valid | 0.5 | 12 | 8 | 4.5 | 0
| Estimate Totals | 15 | 12 | 8 | 4.5 | 0